## Slide 1: Comprehensive Plan Update: Phase 2 Detailed Public Outreach Plan
Maya Teeple, Senior Planner
April 19, 2023

## Slide 2: Today’s Work Session
Work Session # 4
  Scope of work - Nov. 16, 2022, Feb. 15 and Mar. 15, 2023
  Today’s topic - Phase 2 Public Outreach Plan
Request
  Planning Commission Subcommittee to assist with phase 2 outreach (listening sessions)
  Any other feedback on phase 2 public outreach

## Slide 3: Thurston 2045: the County’s Periodic Update
Required to periodically (ten-year cycle) update the comprehensive plan and development regulations
Plans for the next 20 years to 2045
Ensures consistency with the Washington State Growth Management Act
Not a full repeal and replace, or a full re-visioning
Next periodic update due June 30, 2025

## Slide 4: Thurston 2045: Timeline

## Slide 5: Thurston 2045: Phase 2 Outreach Goals
Spread awareness about Thurston 2045 update.
Share information about the current adopted plan.
Gather feedback on what community changes.
Inform community about process and future outreach opportunities.
Share information about what is changing (end of phase 2/early phase 3).
Notes: The draft that we’ve provided as an attachment that details phase 2 is the goal for outreach. How much of it we can achieve will depend on the resources allocated by the BoCC and assistance from the Planning Commission, and priorities of other work we are directed to work on by the Board. If we do not meet every opportunity outlined in the plan, it is not grounds for invalidation of the comprehensive plan update.
Goal of phase 2 is to spread awareness and collect feedback to inform the update. The early outreach will be used to inform the updates to the plan. Staff and consultants will also be working on proposed changes during this year. Specific goals are:
  Make the community aware of the update that is underway, including scope, timeline, and purpose.
  Share information about the current adopted plan.
  Gather feedback on what the community needs to be changed, is still relevant, or if major policies are missing.
  Provide a general timeline for the project and how to stay engaged moving forward.
  Share information on what is changing in the plan (end of phase 2/early phase 3).

## Slide 6: Thurston 2045: Phase 2 Outreach Methods
Project webpage
Thurston 2045 Photo Contest
Surveys
Open Houses
  Online story maps
  General open houses
  Pop-up/Informational Booths
Planning Commission Subcommittee(s)
Listening Sessions
Targeted Presentations
Stakeholder Groups
Throughout Phase 2
Early Phase 2
Late Phase 2

## Slide 7: Thurston 2045: Outreach Methods
Webpage
  Runs through the life of the project
  Lists meetings
  Opportunities for people to learn more about current plan and proposed updates
  Surveys, options to comment, and more
  Has documents as they become available
Notes: Goal: Spread information, collect feedback

## Slide 8: Thurston 2045: Outreach Methods
Open Houses
  Story Map (6-9)
    High-level information about comprehensive plan and topics
    General info about expected areas of change
    Live throughout phase 2, updating in Phase 3 to show proposed changes
    Comment and survey opportunities
  General Open Houses (1-2)
    High-level information about comprehensive plan and topics
    Collect feedback on topics
    Learn about the timeline and opportunities to get involved
  Informational Booths
    Fact sheets available for passers-by
Notes: Goal: Spread information, collect feedback

## Slide 9: Thurston 2045: Outreach Methods
Surveys
  Topic specific surveys with questions to gather specific feedback
  Linked in story maps
  Expected timing June-December
Notes: Goal: Collect feedback

## Slide 10: Thurston 2045: Outreach Methods
Thurston 2045 Photo Contest
  Hold a photo contest, possibly through social media or other platform
  Winner(s) featured in collage of inside cover of Plan
  Consider offering other prize if budget available
Notes: Goal: Spread awareness, get people involved, fun opportunity

## Slide 11: Thurston 2045: Outreach Methods
Planning Commission Subcommittee(s)
  Public Engagement Subcommittee
  Assist with phase 2 outreach – listening sessions
    Review list of stakeholder groups and identify missing players
    Select dates to hold topic-based and general listening sessions
    Ask set of questions, facilitate conversation
    Divide up targeted listening sessions (go to specific underrepresented groups)
      Take notes, provide to staff
    Report back to whole Planning Commission
Notes: Goal: Assist with Phase 2 outreach

## Slide 12: Thurston 2045: Outreach Methods
Planning Commission Subcommittee(s)
  Expected time commitment: 12-22 hours over 5-6 months
    3-4 hours: Subcommittee meetings (1 hour initially, then check ins)
    4-8 hours: Topic-based listening sessions
    2-4 hours: General listening sessions
    2-5 hours: Targeted listening sessions with underrepresented groups
    1 hour: Take and compile notes to send to staff
    1 hour+: Report back to Planning Commission
Notes: Goal: Assist with Phase 2 outreach
Minimum 3 PCers

## Slide 13: Thurston 2045: Outreach Methods
Targeted Presentations
  Later in phase 2
  Staff to present on topics as requested by community groups
  Collect feedback and provide information on updates
Notes: Goal: Assist with Phase 2 outreach

## Slide 14: Thurston 2045: Outreach Methods
Stakeholder Groups
  Later in phase 2
  Topic specific stakeholder group work
  Topics TBD, may include housing
  May request Planning Commissioner(s) to participate
Notes: Goal: Assist with Phase 2 outreach

## Slide 15: Thurston 2045: Phase 2 Timeline
 | 2023 |  |  |  |  |  |  |  |  |  | 2024 | 
 | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb
PC Subcommittee |  |  |  |  |  |  |  |  |  |  |  | 
Informational Booths |  |  |  |  |  |  |  |  |  |  |  | 
Project Webpage |  |  |  |  |  |  |  |  |  |  |  | 
Story Maps |  |  |  |  |  |  |  |  |  |  |  | 
Surveys |  |  |  |  |  |  |  |  |  |  |  | 
General Open House |  |  |  |  |  |  |  |  |  |  |  | 
Listening Sessions |  |  |  |  |  |  |  |  |  |  |  | 
Photo Contest |  |  |  |  |  |  |  |  |  |  |  | 
Targeted Presentations |  |  |  |  |  |  |  |  |  |  |  | 
Stakeholder Groups |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 16: Thurston 2045: Phase 2 Public Participation
Discussion
  Public engagement subcommittee?
  Other questions, comments, concerns?
Notes: Goal: Assist with Phase 2 outreach

## Slide 17
  Thank you!
  Maya Teeple
  Senior Planner
  360-545-2593
  Maya.Teeple@co.Thurston.wa.us
  www.Thurston2045.org
Notes: Goal: Assist with Phase 2 outreach